## doc-history
RELEASE | DATE | DESCRIPTION
r1 | 2024-04-23 | 1. Initial release 2. Update Sprint 1 Description 3. Add Sprint 1 TestData (TASK_BASE) and PBI1-2 test cases 4. Trim Task's Title and Desc, merge TC-PBI2 4 and 5
r1.0.1 | 2024-04-23 | 1. Update API Spec

## Non-functional Requirements
Release 1 | Release 1
1 | There is only one task board.
2 | Development team is the owner of the board.
3 | There is no user authentication/authorization support yet, anyone with access to the system can view and modify the board.
4 | The board must be accessible from within KMUTT network (but not limited to).
5 | The system uses UTF-8 character-encoding.
6 | The system supports ICT (Asia/Bangkok) time-zone.

## Product Backlog
PBI # | PBI NAME | PBI DESCRIPTION / CONDITIONS | Type | Priority | Size | Sprint
1 | VIEW-TASK-TABLE VIEW | 1. List all task in table view, with no pagination. 2. The table shows task: Title, Assignees, Status. 3. The task is sorted ascending order of created time. 4. If there is no task in the board, a table with no record is shown. | ● Must-have | 1 |  | 1
2 | VIEW-TASK-DETAIL | 1. When the user click on task's title, the task's detail is shown in a modal window. 2. Task's detail includes Title, Description, Assignees, Status, Created date, and Updated date. 3. If task's description is null or empty, the statement 'No description provided' is shown in italic and grey. 3.1 If task assignees is null or empty, the statement 'Unassigned' is shown in italic and grey. 4. The dates are shown in local timezone (with timezone identifier such as 'Asia/Bangkok') 5. If the requested task (id) does not exist, the backend returns status code 404 FE shows message "The requested task does not exist" and redirects to previous page upon confirmation to close the message window. | ● Must-have | 2 |  | 1
3 | ADD-TASK-BASIC | 1. When the user click on "Add" button, the task detail modal window is shown. 2. The user can add the Task's details: Title [REQUIRED], Description [OPTIONAL], Assignees [OPTIONAL], Status [default: No Status] 3. DB: auto inserts Created date and Updated date (current date, time), these are NOT provided by BE 4. BE returns status code; FE shows user appropriate message 5. FE Shows task table with added task | ● Must-have | 3 |  | 2
4 | DELETE-TASK | 1. When the user click on "Delete" for a task, a confirmation modal window is shown showing taskTitle to be deleted. "Confirm" and "Cancel" options are provided. 2. When "Confirm", BE deletes task and provides response 3. BE provides response code; FE shows user appropriate message 4. FE shows updated task table | ● Must-have | 4 |  | 2
5 | EDIT-TASK-BASIC | 1. When the user clicks on "Edit" button for a task, the Task-Detail is shown and all fields are editable, with options to "Save" or "Cancel" 2. BE returns status code, and reason 3. FE shows response from BE with user appropriate message 4. If successful FE, shows updated task details. 5. User can click "Close" or "Back" to return to Task Table view. 6. if the task (id) does not exists, BE returns 404 and FE behaves appropriately | ● Must-have | 5 |  | 2
6 | ADD-STATUS |  | ● Must-have | 6 |  | 3
7 | EDIT-STATUS |  | ● Must-have | 7 |  | 3
8 | DELETE-STATUS |  | ● Must-have | 8 |  | 3
9 | NESTED-PUBLIC-PATH |  | ● Should-have | 9 |  | 3
10 | SORT-TASK-BY-STATUS-TABLE-VIEW |  | ● Should-have | 10 |  | 4
11 | FILTER-TASK-BY-STATUS-TABLE-VIEW |  | ● Should-have | 11 |  | 4
12 | LIMIT-TASKS-IN-STATUS |  | ● Should-have | 12
13 | VALIDATE-INPUT-FE-BASIC |  | ● Should-have | 13 |  | 4
14 | VALIDATE-INPUT-BE-BASIC |  | ● Could-have | 14 |  | 4

## Attributes
task : v1 [PBI1–PBI5]
Attribute Name | Description / Constraints | Example
taskTitle | Task name : UTF-8 TEXT; Limit to 100 characters; NOT NULL; NOT EMPTY; Leading and trailing whitespaces are trimmed; | design API specs for PBI1–2
taskDescription | Task description : UTF-8 TEXT; Limit to 500 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are trimmed; | need to specify endpoints, request body, response body, status
taskAssignees | Task assignees : UTF-8 TEXT; Limit to 30 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are trimmed. | Pang; Pong;
taskStatus | Task status : ENUM of {No Status, To Do, Doing, Done}; NOT NULL; The default value is 'No Status'; | To Do
createdOn | Task creation date/time (on DBMS) : DATETIME; NOT NULL; | 2024-04-19 01:00:00
updatedOn | Task last update date/time (on DBMS) : DATETIME; When a task is created, updatedOn is the same as createdOn; NOT NULL; | 2024-04-19 01:00:00
task : v2 [PBI6 – ]
Attribute Name | Description / Constraints | Example
taskTitle | Task name : UTF-8 TEXT; Limit to 100 characters; NOT NULL; NOT EMPTY; Leading and trailing whitespaces are allowed; | design API specs for PBI1–2
taskDescription | Task description : UTF-8 TEXT; Limit to 500 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are allowed; | need to specify endpoints, request body, response body, status
taskAssignees | Task assignees : UTF-8 TEXT; Limit to 30 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are trimmed. | Pang; Pong;
taskStatus | Task status; Applicable statuses are stored in status table; NOT NULL; The default value is 'No Status'; | To Review
createdOn | Task creation date/time (on DBMS) : DATETIME; NOT NULL; | 2024-04-19 01:00:00
updatedOn | Task last update date/time (on DBMS) : DATETIME; When a task is created, updatedOn is the same as createdOn; NOT NULL; | 2024-04-20 18:00:00
status : v1 [PBI6 - ]
Attribute Name | Description / Constraints | Example
statusName | Status name : UTF-8 TEXT; Limit to 50 characters; NOT NULL; NOT EMPTY; Leading and trailing whitespaces are trimmed; | To Do
statusDescription | Status description : UTF-8 TEXT; Limit to 200 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are allowed; | This item hasn't been started

## TestData
Data Set | <empty table>
TASKS
taskId | taskTitle | taskDescription | taskAssignees | taskStatus | createdOn | updateOn
Data Set | TASK_BASE
TASKS
taskId | taskTitle | taskDescription | taskAssignees | taskStatus | createdOn | updatedOn | Note
1 | TaskTitle1TaskTitle2TaskTitle3TaskTitle4TaskTitle5TaskTitle6TaskTitle7TaskTitle8TaskTitle9TaskTitle0 | Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti1Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti2Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti3Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti4Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti5 | Assignees1Assignees2Assignees3 | No Status | 22/4/2024 09:00:00 +00:00 | 22/4/2024 09:00:00 +00:00 | Max values, "No Status"
2 | Repository | <empty> | <empty> | To Do | 22/4/2024 09:05:00 +00:00 | 22/4/2024 14:00:00 +00:00 | empty fields, "To Do"
3 | ดาต้าเบส | ສ້າງຖານຂໍ້ມູນ | あなた、彼、彼女 (私ではありません) | Doing | 22/4/2024 09:10:00 +00:00 | 25/4/2024 00:00:00 +00:00 | "Doing", Non-English characters, non-local datetime
4 | _Infrastructure_ | _Setup containers_ | ไก่งวง กับ เพนกวิน | Done | 22/4/2024 09:15:00 +00:00 | 22/4/2024 10:00:00 +00:00 | "Done", 5 leadin/trailing Whitespace for Title and Description

## AcceptanceTest
Test ID | Test Scenario | Test Data | Test Steps | Expected Results | Notes | BE tests
TC-PBI1-VIEW-TASK-TABLE VIEW-1 | normal - task table is empty | <task table empty> | 0. prepare empty TASK table 1. Open task view page at /task | 1. FE sends request to BE 2. BE returns status code 200 with response body = '[]' (view in browser Inspector) 3. FE shows task table with column headers and no task list |  | How to test CORS
TC-PBI1-VIEW-TASK-TABLE VIEW-2 | normal - task table has entries - complete entry - no asignees - all status | TASK_BASE | 0. Load TASK_BASE test data 1. Open task view page at /task | 1. FE sends request to BE 2. BE returns status code 200 and all task entries 3. FE shows task table with column headers and 4 task entries 4. Task Title order shows as indicated to the right >> | 1. TaskTitle1TaskTitle2TaskTitle3TaskTitle4TaskTitle5TaskTitle6TaskTitle7TaskTitle8TaskTitle9TaskTitle0 2. Repository 3. ดาต้าเบส 4. _Infrastructure_
TC-PBI2-VIEW-TASK-DETAIL-1 | normal - all fields available - datetime local time - max fields: taskTitle, taskDescription, taskAssignees - taskStatus is "No Status" | TASK_BASE | 0. Load TASK_BASE test data 1. Open task details for task TaskTitle1... 1.1 verify max character limits for Title, Description, Assignees 1.2 verify Status "No Status" 1.3 verify datetime with timezone identifier | 1. Task details are shown with max character limits for Title, Description, Assignees 2. datetime for BOTH createdOn AND updatedOn are shown as 22/04/2024 16:00:00 (Asia/Bangkok) 3. taskStatus is shown as "No Status" 4. BE returns 200 and task details
TC-PBI2-VIEW-TASK-DETAIL-2 | normal - empty Description and Assignees - taskStatus of "To Do" | TASK_BASE | 1. Open task details for task Repository 1.1 verify Description and Assignees 1.2 verify Status is "To Do" | 1. Task details are shown 2. Description is shown as "No Description Provided" in grey italic 3. Assignees is shown as "Unassigned" in grey italic 4. Status is "To Do" 5. BE returns 200 and task details
TC-PBI2-VIEW-TASK-DETAIL-3 | normal - non-English characters - taskStatus of "Doing" | TASK_BASE | 1. Open task details for task ดาต้าเบส 1.1 verify Title, Description and Assignees is non-English 1.2 verify Status is "Doing" | 1. Title, Details, and Assignees are shown in non-English characters correctly 2. Status is "Doing" 3. BE returns 200 and task details
TC-PBI2-VIEW-TASK-DETAIL-4 | normal - view different time zone - taskStatus of "Done" | TASK_BASE | 1. In task detail view for task _Infrastructure_ 2. change the browser's timezone to Australia/Sydney (+10:00) (see link on the right) 2.1 verify the time shown 2.2 verify Status is "Done" | 1. datetime is shown as 22/4/2024 19:15:00 (Australia/Sydney) and 22/4/2024 20:00:00 (Australia/Sydney) 2. Status is "Done" | https://www.browserstack.com/guide/change-time-zone-in-chrome-for-testing
TC-PBI2-VIEW-TASK-DETAIL-5 | failed - view task with invalid ID | TASK_BASE | 1. Open task view page at /task/100 | 1. FE shows User Appropriate message "The requested task does not exist" and when the message is closed redirects to the TaskList view (/task) 2. BE returns 404

## API Spec
API Specifications for sprint-1 (update-1)
http://ip23<TEAM-CODE>.sit.kmutt.ac.th
Server:
URI: