## doc-history
RELEASE | DATE | DESCRIPTION
| 2024-04-17 | Initial release
| 2024-04-23 | Sprint 1, TestData TASK_BASE and PBI1-2 test cases, trim Title and Desc, merge TC-PBI2 cases 4 and 5
| 2024-04-23 | Update API Spec for Sprint 1
| 2024-04-29 | Updated PBI 3-5, with test cases; added TASK_BASE_ADD test data
| 2024-05-01 | Update PBI3 description to state the behavior of "Save" button Minor update of PBI4 description Update PBI5 description to state the behavior of "Save" button and change the error message on the FE Update TestData to use 'Not Specified - Null' instead of 'Empty'.
| 2024-05-06 | TC for PBI 6-8 | sy
| 2024-05-07 | update STATUS_BASE, TC, add Table Data along side TC; grey italics for NULL description | sy
| 11-12/5/24 | update PBI 6-7 description to cover trim on BE and FE sends NULL on empty, optional field update test cases for PBI 6-9 to correspond to description and cover all cases (remove validation) | or
r1 | 2024-04-23 | 1. Initial release 2. Update Sprint 1 Description 3. Add Sprint 1 TestData (TASK_BASE) and PBI1-2 test cases 4. Trim Task's Title and Desc, merge TC-PBI2 4 and 5
r1.0.1 | 2024-04-23 | 1. Update API Spec
r2 | 2024-05-02 | Updated PBI 3-5, with test cases; added TASK_BASE_ADD test data 1. update PBI3 description to state the behavior of "Save" button 2. update PBI4 description on the message 3. update PBI5 description to state the behavior of "Save" button and change the error message on the FE 4. update TestData to use 'Not Specified - Null' instead of 'Empty'.
r3 | 2024-05-12 | Updated PBI 6-9, with test cases; added STATUS_BASE and TASK_BASE_ADD test data 1. On PBI 8, update the message for 'transfer and delete' to include the number of tasks under to-delete status
r4 | 2024-05-19 | Updated PBI 10-14, with test cases and test data;

## Non-functional Requirements
Release 1 | Release 1
1 | There is only one task board.
2 | Development team is the owner of the board.
3 | There is no user authentication/authorization support yet, anyone with access to the system can view and modify the board.
4 | The board must be accessible from within KMUTT network (but not limited to).
5 | The system uses UTF-8 character-encoding.
6 | The system supports ICT (Asia/Bangkok) time-zone.

## Product Backlog
PBI # | PBI NAME | PBI DESCRIPTION / CONDITIONS | Type | Priority | Size | Sprint
1 | VIEW-TASK-TABLE VIEW | 1. List all task in table view, with no pagination. 2. The table shows task: Title, Assignees, Status. 3. The task is sorted ascending order of created time. 4. If there is no task in the board, a table with no record is shown. | ● Must-have | 1 |  | 1
2 | VIEW-TASK-DETAIL | 1. When the user click on task's title, the task's detail is shown in a modal window. 2. Task's detail includes Title, Description, Assignees, Status, Created date, and Updated date. 3. If task's description is NULL, the statement 'No description provided' is shown in italic and grey. <Empty> is converted to NULL 3.1 If task assignees is NULL, the statement 'Unassigned' is shown in italic and grey. 4. The dates are shown in local timezone (with timezone identifier such as 'Asia/Bangkok') 5. If the requested task (id) does not exist, the backend returns status code 404 FE shows message "The requested task does not exist" and redirects to previous page upon confirmation to close the message window. | ● Must-have | 2 |  | 1
3 | ADD-TASK-BASIC | 1. When the user clicks on "Add" button, the task detail modal window is shown with options to "Save" and "Cancel". "Save" is enabled only if the taskTitle is NOT empty. 1.1 The user can add the Task's details: Title [REQUIRED], Description [OPTIONAL], Assignees [OPTIONAL], Status [default: No Status] 1.1.1 If task description is NULL or empty, the statement 'No description provided' is shown in italic and grey. 1.2 FE does NOT trim while the user enters data. FE must trim task details before sending to BE. 1.3 On "Save" FE sends request to BE, On "Cancel" returns to previous page. 2. BE assumes that the request body contains valid fields (validation will be implemented in PBI14.) 3. DB: inserts data and auto inserts createdOn and updatedOn (current date, time), dateTime data are NOT provided by BE 4. If DB insert is successful, BE returns status code 201 and FE shows "The task has been successfully added" 5. FE Shows updated TableView with added task | ● Must-have | 3 |  | 2
4 | DELETE-TASK | 1. When the user click on "Delete" for a task, a confirmation modal window is shown showing task running number (in the table) and taskTitle to be deleted. "Confirm" and "Cancel" options are provided. 2. When "Confirm", FE sends request to BE to delete the specified task. 3. On DB deletion success, BE returns status code 200, FE shows "The task has been deleted" 3.1 On failed deletion of invalid taskID, BE returns status code 404, FE shows "An error has occurred, the task does not exist." 4. FE shows updated task table | ● Must-have | 4 |  | 2
5 | EDIT-TASK-BASIC | 1. When the user clicks on "Edit" button for a task, a modal window with Task-Detail is shown and all fields, except DateTime fields, are editable, with options to "Save" or "Cancel". "Save" is enabled only if the form is modified by the user. 2. FE does NOT trim any field while the user enters the data on these fields. FE must trim task details before sending to BE. 3. On "Save", FE sends request to BE. On "Cancel", no request is made to BE, FE then returns to previous page. 4. On successful update, FE shows "The task has been updated" and returns to the previous page. 5. On failed update (invalid taskID), BE returns 404 status code and FE shows "An error has occurred, the task does not exist." | ● Must-have | 5 |  | 2
6 | ADD-STATUS (TC includes VIEW) | 1. When the user clicks on "Manage Status" menu, the Status table listing existing statuses is shown with statusName and statusDescription. 1.1 If statusDescription is NULL, the statement 'No description provided' is shown in italic and grey. 2. User has choice to Add, Edit, or Delete Status. The No Status status cannot be edited or deleted. 3. When "Add" is clicked, a modal window to add a new status is shown, with options to "Save" or "Cancel". "Save" is enabled only if the statusName is NOT empty. 4. User enter status Name [Required] and Description [Optional]. The statusName is 'NOT NULL', 'NOT EMPTY', 'UNIQUE' (uniqueness is NOT tested in this PBI). The statusDescription is 'NULLABLE' and 'NOT EMPTY'. 4.1 FE does NOT trim any field while the user enters the data on these fields. FE must trim status details before sending to BE. 4.2 If the user does not specify status description (statusDescription is EMPTY), FE sends 'NULL' to BE. 5. When user click "Save", FE sends request to BE 5.1 BE must trim statusName and statusDescription before inserting to DB. 5.2 On success, BE returns 200, FE shows a message "The status has been added" and then returns the previous page to show the updated Status Table 5.3 On failure, BE returns 400 or 500, FE shows a message "An error has occurred, the status could not be added." and then returns the previous page. The Status Table is unchanged. | ● Must-have | 6 |  | 3
7 | EDIT-STATUS (TC includes VIEW-STATUS) | 1. When the user clicks on "Edit" button for a Status, the Edit-Status modal window is shown and all fields are editable, with options to "Save" or "Cancel" 1.1 the "No Status" status cannot be edited 1.2 "Save" is enabled only if the form is modified by the user and status name is not empty 1.3 FE does NOT trim any field while the user enters the data on these fields. FE must trim status details before sending to BE. 1.4 If the user does not specify status description (statusDescription is EMPTY), FE sends 'NULL' to BE. 1.5 BE must trim statusName and statusDescription before updating DB. 2. On “Save”, FE sends request to BE. On “Cancel”, no request is made to BE, FE then returns to previous page. 3. On successful update, FE shows “The status has been updated” and returns to the previous page. The status table and task table are shown with the updated name or description. 4. On failed update (invalid statusID), BE returns 404 status code and FE shows “An error has occurred, the status does not exist.” 5. User can click “Close” or “Back” to return to previous page. | ● Must-have | 7 |  | 3
8 | DELETE-STATUS | 1. The "No Status" status cannot be deleted 2. If there is no task under the specified status, FE opens modal window asking the user "Do you want to delete <statusName> status?" "Confirm" and "Cancel" options are provided. 2.1 When "Confirm", FE sends request to BE to delete the status. If the deletion is successful, BE returns 200 and FE shows “The status has been deleted”. In the case the status does not exist, BE returns 404 and FE shows “An error has occurred, the status does not exist.” 2.2 When “Cancel”, FE does not send request to BE and returns to previous page 3. If there are tasks in the specified status, FE opens modal window asking user “There are <number of tasks> tasks in <statusName> status. In order to delete this status, the system must transfer tasks in this status to existing status. Transfer tasks to [drop-down of existing statuses] ” “Transfer and Delete” and “Cancel” options are provided. FE does not offer/allow the user to transfer tasks to to-delete status. 3.1 “Transfer and Delete” is enable only when destination status is selected (there is no default) 3.2 When “Transfer and Delete”, FE sends request to BE to transfer tasks in to-delete status to destination status and delete the to-delete status. If the transfer and deletion is successful, BE returns 200 and FE shows “<number of tasks> task(s) have been transferred and the status has been deleted”. In the case the status is no longer exist, BE returns 404 and FE shows “An error has occurred, the status does not exist.” 3.3 When “Cancel”, FE does not send request to BE and returns to previous page 4. FE shows updated Status table | ● Must-have | 8 |  | 3
9 | NESTED-PUBLIC-PATH | 1. The system must be accessible from internet (without VPN). 2. This includes frontend and backend, but not database. 3. The database must be accessible within the server only. 4. The public url for each system is ‘http://intproj23.sit.kmutt.ac.th/<TEAMCODE>’, e.g., ‘http://intproj23.sit.kmutt.ac.th/sy1’ 5. 'intproj23.sit.kmutt.ac.th' is maintained by the school admin. 6. The team may configure reverse proxy on the host machine to handle multiple versions and CORS issue better. | ● Should-have | 9 |  | 3
10 | SORT-TASK-BY-STATUS-TABLE-VIEW | 1. On task list page, when click on "Sort By Status" the tasks in the table are sorted by status name in alphabetical order or in reverse order if clicked again. 2. The user can cancel sorting and revert back to default sort (createdDate) 3. When there is a change in sort setting (alphabetical/reverse/default), FE updates task table accordingly. 4. Based on the assumption that FE can get all tasks, the sort can be performed solely on the FE. There is no need to implement this feature on the BE (there will be no postman test, however, the team may choose to implement this on the BE) | ● Should-have | 10 |  | 4
11 | FILTER-TASK-BY-STATUS-TABLE-VIEW | 1. On task list page, "Filter" button allows selection of statuses for filtering. 1.1 Multiple statuses can be selected at the same time 1.2 Initially, all statuses are selected 2. If there is a change in selection, FE sends request to BE for filtering 3. The tasks table shows tasks in the selected statuses 3.1 The tasks are sorted based on current sort setting (PBI10). 4. BE handles invalid filter requests 4.1 invalid statusID: return 200 and empty array (return array for valid statusID) 4.2 return 400 if request to sort by other fields (if implemented with the sort field as a parameter) | ● Should-have | 11 |  | 4
12 | LIMIT-TASKS-IN-STATUS | 0. Status "Done" cannot be Edited or Deleted. This status is considered as the final state. 1. The user can enable/disable a maximum limit of 10 tasks that apply to all statuses except for "No Status" and "Done". The limit value should be stored in database along with limit-flag. The default limit-flag value is 'false' or 'disable'. 2. On Status Management page, an option is provided to Enable/Disable status limit 2.1 On click "Enable" show message "The Kanban board will limit the number of tasks in each status to 10."; On confirm Enable, a message is shown "The Kanban board now limits 10 tasks in each status" [Change: No task_status transfer, tasks remain in their statuses even if exceed limit] 2.1.1. For statuses that exceed the limit, show a list of status with number of tasks in each status. With a message "These statuses that have reached the task limit. No additional tasks can be added to these statuses at this time." 3. Add Task and Edit Task_Status cannot make the number of task in a status exceed the "limit" value. 3.1 The limit Enable/Disable state is shown on AddTask and EditTask modal 3.2 On over limit, provide an appropriate message. "The status <statusName> will have too many tasks. Please make progress and update status of existing tasks first." 4. When deleting a "to-delete" status with existing tasks, if the transfer-destination status plus the number of tasks in "to-delete" status exceeds the limit, FE shows the message "Cannot transfer to <destination-status> status since it will exceed the limit. Please choose another status to transfer to." and returns/stays on "transfer and delete" modal. If there is no possible status to transfer to, the user can "Cancel" the action. 5. On Disable limit, show a message "The Kanban board has disabled the task limit in each status." 6. BE handles invalid limit-related requests (only when the limit is enable) 6.1 Add/Edit task and the status has reached the limit: return 400 with message {"field": "status", "message": "the status has reached the limit"} 6.2 Delete and transfer, the destination status will be over the limit after transfer, return 400 with message {"field": "status", "message": "the destination status cannot be over the limit after transfer"} | ● Should-have | 12 |  | 4
13 | VALIDATE-INPUT-FE-BASIC | Tasks 1. Maximum field size for Add and Edit Task: taskTitle (100), taskDescription(500), taskAssignees (30) (new test case >> exceed max): can paste more than max character limit, but cannot Save Statuses 1. Cannot edit/delete "Done", FE does not have button to edit/delete 2. Maximum field size for Add and Edit Status: statusName (50), statusDescription (200) (new test case, exceed max): can paste more than max character limit, but cannot save 3. statusName must be UNIQUE, else cannot Add/Edit succesfully (new): show message "Status name must be uniques, please choose another name.", stay on add/edit modal. 3.1 The validation must be performed on FE based on status records retrieved. | ● Should-have | 13 |  | 4
14 | VALIDATE-INPUT-BE-BASIC | Tasks 1.1 Cannot Add/Edit without REQUIRED taskTitle 1.2 Add/Edit that exceed maximum field size: return 400, with message for each field. For example, {"field": "<field name>", "message": "size must be between 0 and 30"} 1.3 Add/Edit with invalid statusID: return 400 with message {"field": "status", "message": "does not exist"} Status 2.1 Cannot Add/Edit without REQUIRED statusName 2.2 Cannot Add/Edit with non-UNIQUE statusName 2.3 Add/Edit that exceed maximum field size: return 400, with message for each field. For example, {"field": "<field name>", "message": "size must be between 1 and 50"} 2.4 Cannot Edit or Delete "No Status" and "Done" 2.5 Cannot Delete a status that still have tasks (has not transferred): return 400 2.6 Cannot transfer a task to a status with invalid statusID (source, destination) 2.7 Cannot transfer a task to a status with same source and and destination statusID | ● Could-have | 14 |  | 4

## Attributes
task : v1 [PBI1–PBI5]
Attribute Name | Description / Constraints | Example
taskTitle | Task name : UTF-8 TEXT; Limit to 100 characters; NOT NULL; NOT EMPTY; Leading and trailing whitespaces are trimmed; | design API specs for PBI1–2
taskDescription | Task description : UTF-8 TEXT; Limit to 500 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are trimmed; | need to specify endpoints, request body, response body, status
taskAssignees | Task assignees : UTF-8 TEXT; Limit to 30 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are trimmed. | Pang; Pong;
taskStatus | Task status : ENUM of {No Status, To Do, Doing, Done}; NOT NULL; The default value is 'No Status'; | To Do
createdOn | Task creation date/time (on DBMS) : DATETIME; NOT NULL; | 2024-04-19 01:00:00
updatedOn | Task last update date/time (on DBMS) : DATETIME; When a task is created, updatedOn is the same as createdOn; NOT NULL; | 2024-04-19 01:00:00
task : v2 [PBI6 – ]
Attribute Name | Description / Constraints | Example
taskTitle | Task name : UTF-8 TEXT; Limit to 100 characters; NOT NULL; NOT EMPTY; Leading and trailing whitespaces are trimmed; | design API specs for PBI1–2
taskDescription | Task description : UTF-8 TEXT; Limit to 500 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are trimmed; | need to specify endpoints, request body, response body, status
taskAssignees | Task assignees : UTF-8 TEXT; Limit to 30 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are trimmed. | Pang; Pong;
taskStatus | Task status; Applicable statuses are stored in status table; NOT NULL; The default value is 'No Status'; | To Review
createdOn | Task creation date/time (on DBMS) : DATETIME; NOT NULL; | 2024-04-19 01:00:00
updatedOn | Task last update date/time (on DBMS) : DATETIME; When a task is created, updatedOn is the same as createdOn; NOT NULL; | 2024-04-20 18:00:00
status : v1 [PBI6 - ]
Attribute Name | Description / Constraints | Example
statusName | Status name : UTF-8 TEXT; Limit to 50 characters; NOT NULL; NOT EMPTY; UNIQUE Leading and trailing whitespaces are trimmed; | To Do | 50 characters is too long, maybe 20
statusDescription | Status description : UTF-8 TEXT; Limit to 200 characters; OPTIONAL; NOT EMPTY; Leading and trailing whitespaces are trimmed; | This item hasn't been started
statusLimit [PBI10 -14 ]
Attribute Name | Description / Constraints | Example
statusLimit | TRUE¦FALSE Default value = FALSE | FALSE

## TestData
Data Set | <empty table>
TASKS
taskId | taskTitle | taskDescription | taskAssignees | taskStatus | createdOn | updateOn
Data Set | TASK_BASE
TASKS
taskId | taskTitle | taskDescription | taskAssignees | taskStatus | createdOn | updatedOn | Note
1 | TaskTitle1TaskTitle2TaskTitle3TaskTitle4TaskTitle5TaskTitle6TaskTitle7TaskTitle8TaskTitle9TaskTitle0 | Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti1Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti2Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti3Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti4Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti5 | Assignees1Assignees2Assignees3 | No Status | 22/4/2024 09:00:00 +00:00 | 22/4/2024 09:00:00 +00:00 | Max values, "No Status"
2 | Repository | <not specified - NULL> | <not specified - NULL> | To Do | 22/4/2024 09:05:00 +00:00 | 22/4/2024 14:00:00 +00:00 | empty fields, "To Do"
3 | ดาต้าเบส | ສ້າງຖານຂໍ້ມູນ | あなた、彼、彼女 (私ではありません) | Doing | 22/4/2024 09:10:00 +00:00 | 25/4/2024 00:00:00 +00:00 | "Doing", Non-English characters, non-local datetime
4 | _Infrastructure_ | _Setup containers_ | ไก่งวง กับ เพนกวิน | Done | 22/4/2024 09:15:00 +00:00 | 22/4/2024 10:00:00 +00:00 | "Done", 5 leadin/trailing Whitespace for Title and Description
TASKS | TASK_BASE_ADD
taskId | taskTitle | taskDescription | taskAssignees | taskStatus | createdOn | updatedOn | Note
5 | DevSecOps | <not specified - NULL> | <not specified - NULL> | <not specified> |  |  | When test FE, the user does not specify taskStatus, and FE sends 'No Status'. When test BE, do not send taskStatus, or send taskStatus=NULL to the BE.
6 | DevSecOps1DevSecOps2DevSecOps3DevSecOps4DevSecOps5DevSecOps6DevSecOps7DevSecOps8DevSecOps9DevSecOps0 | Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti1Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti2Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti3Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti4Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti5 | Assignees1Assignees2Assignees3 | To Do
7 | _Front End_ | _fix CSS on landing page_ | _ปุยฝ้าย กับ เสือดาว_ | Done
STATUS | STATUS_BASE
statusId | statusName | statusDescription
1 | No Status | The default status
2 | To Do | <not specified - NULL>
3 | Doing | Being worked on
4 | Done | Finished
STATUS | STATUS_BASE_ADD
statusId | statusName | statusDescription | Note
5 | Waiting | <not specified - NULL>
6 | Maximum001Maximum002Maximum003Maximum004Maximum005 | Maximum001Maximum002Maximum003Maximum004Maximum005Maximum006Maximum007Maximum008Maximum009Maximum100Maximum001Maximum002Maximum003Maximum004Maximum005Maximum006Maximum007Maximum008Maximum009Maximum200 | name: 50, desc 200 characters |  | << later the description is changed to NULL
7 | _trim_ | _trim_
8 | <not specified - NULL> | No name | BE test only, statusName not provided
| PUBLIC_URL |  | Example
FE | http://intproj23.sit.kmutt.ac.th/<TEAMCODE> |  | http://intproj23.sit.kmutt.ac.th/sy1
BE | http://intproj23.sit.kmutt.ac.th:8080/<TEAMCODE>/v2/tasks |  | http://intproj23.sit.kmutt.ac.th:8080/sy1/v2/tasks
| OR http://intproj23.sit.kmutt.ac.th/<TEAMCODE>/api/v2/tasks |  | http://intproj23.sit.kmutt.ac.th/sy1/api/v2/tasks
PBI13, PBI14: Validation and Exception Handling
STATUS | STATUS_BASE_ADD
4 | <not specified - NULL> | No name | BE test only, statusName not provided
<100> | Non-existing-status |  | BE test only, status(id) = 100
STATUS | STATUS_SORT_FILTER
statusId | statusName | statusDescription
1 | No Status | A status has not been assigned
2 | To Do | The task is included in the project
3 | In Progress | The task is being worked on
4 | Reviewing | The task is being reviewed
5 | Testing | The task is being tested
6 | Waiting | The task is waiting for a resource
7 | ​Done | The task has been completed
TASK | TASK_SORT_FILTER
taskId | taskTitle | taskDescription | taskAssignees | taskStatus | createdOn | updatedOn
1 | NS01 |  |  | No Status | 14/5/2024 09:00:00 +00:00 | 14/5/2024 09:00:00 +00:00
2 | TD01 |  |  | To Do | 14/5/2024 09:10:00 +00:00 | 14/5/2024 09:10:00 +00:00
3 | IP01 |  |  | In Progress | 14/5/2024 09:20:00 +00:00 | 14/5/2024 09:20:00 +00:00
4 | TD02 |  |  | To Do | 14/5/2024 09:30:00 +00:00 | 14/5/2024 09:30:00 +00:00
5 | DO01 |  |  | Done | 14/5/2024 09:40:00 +00:00 | 14/5/2024 09:40:00 +00:00
6 | IP02 |  |  | In Progress | 14/5/2024 09:50:00 +00:00 | 14/5/2024 09:50:00 +00:00
TASK | TASK_LIMIT_BASE
taskId | taskTitle | taskDescription | taskAssignees | taskStatus | createdOn | updatedOn
7 | NS02 |  |  | No Status
8 | NS03 |  |  | No Status
9 | NS04 |  |  | No Status
10 | NS05 |  |  | No Status
11 | NS06 |  |  | No Status
12 | NS07 |  |  | No Status
13 | NS08 |  |  | No Status
14 | NS09 |  |  | No Status
15 | NS10 |  |  | No Status
16 | DO02 |  |  | Done
17 | DO03 |  |  | Done
18 | DO04 |  |  | Done
19 | DO05 |  |  | Done
20 | DO06 |  |  | Done
21 | DO07 |  |  | Done
22 | DO08 |  |  | Done
23 | DO09 |  |  | Done
24 | DO10 |  |  | Done
25 | IP03 |  |  | In Progress
26 | IP04 |  |  | In Progress
27 | IP05 |  |  | In Progress
28 | IP06 |  |  | In Progress
29 | IP07 |  |  | In Progress
30 | IP08 |  |  | In Progress
31 | IP09 |  |  | In Progress
32 | IP10 |  |  | In Progress
33 | TD03 |  |  | To Do
34 | TD04 |  |  | To Do
35 | TD05 |  |  | To Do
36 | TD06 |  |  | To Do
37 | TD07 |  |  | To Do
38 | TD08 |  |  | To Do
39 | TD09 |  |  | To Do
40 | RE01 |  |  | Reviewing
41 | TE01 |  |  | Testing
42 | WA01 |  |  | Waiting
TASK | TASK_LIMIT_ADD
taskId | taskTitle | taskDescription | taskAssignees | taskStatus | createdOn | updatedOn
40 | NS11 |  |  | No Status
41 | DO11 |  |  | Done
42 | TD10 |  |  | To Do
43 | IP11 |  |  | In Progress
44 | TD11 |  |  | To Do
45 | TD12 |  |  | To Do
TASK | TASK_ADD_>MAX
taskId | taskTitle | taskDescription | taskAssignees | taskStatus | createdOn | updatedOn
46 | TaskTitle1TaskTitle2TaskTitle3TaskTitle4TaskTitle5TaskTitle6TaskTitle7TaskTitle8TaskTitle9TaskTitle0+++++ | Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti1Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti2Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti3Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti4Descripti1Descripti2Descripti3Descripti4Descripti5Descripti6Descripti7Descripti8Descripti9Descripti5+++++ | Assignees1Assignees2Assignees3+++++
STATUS | STATUS_ADD_>MAX
statusId | statusName | statusDescription
8 | Maximum001Maximum002Maximum003Maximum004Maximum005+++++ | Maximum001Maximum002Maximum003Maximum004Maximum005Maximum006Maximum007Maximum008Maximum009Maximum100Maximum001Maximum002Maximum003Maximum004Maximum005Maximum006Maximum007Maximum008Maximum009Maximum200+++++

## AcceptanceTest
Test ID | Test Scenario | Test Data | Test Steps | Expected Results | Notes | BE tests
TC-PBI1-VIEW-TASK-TABLE VIEW-1 | normal - task table is empty | <task table empty> | 0. prepare empty TASK table 1. Open task view page at /task | 1. FE sends request to BE 2. BE returns status code 200 with response body = '[]' (view in browser Inspector) 3. FE shows task table with column headers and no task list |  | How to test CORS
TC-PBI1-VIEW-TASK-TABLE VIEW-2 | normal - task table has entries - complete entry - no asignees - all status | TASK_BASE | 0. Load TASK_BASE test data 1. Open task view page at /task | 1. FE sends request to BE 2. BE returns status code 200 and all task entries 3. FE shows task table with column headers and 4 task entries 4. Task Title order shows as indicated to the right >> | 1. TaskTitle1TaskTitle2TaskTitle3TaskTitle4TaskTitle5TaskTitle6TaskTitle7TaskTitle8TaskTitle9TaskTitle0 2. Repository 3. ดาต้าเบส 4. _Infrastructure_
TC-PBI2-VIEW-TASK-DETAIL-1 | normal - all fields available - datetime local time - max fields: taskTitle, taskDescription, taskAssignees - taskStatus is "No Status" | TASK_BASE | 0. Load TASK_BASE test data 1. Open task details for task TaskTitle1... 1.1 verify max character limits for Title, Description, Assignees 1.2 verify Status "No Status" 1.3 verify datetime with timezone identifier | 1. Task details are shown with max character limits for Title, Description, Assignees 2. datetime for BOTH createdOn AND updatedOn are shown as 22/04/2024 16:00:00 (Asia/Bangkok) 3. taskStatus is shown as "No Status" 4. BE returns 200 and task details
TC-PBI2-VIEW-TASK-DETAIL-2 | normal - empty Description and Assignees - taskStatus of "To Do" | TASK_BASE | 1. Open task details for task Repository 1.1 verify Description and Assignees 1.2 verify Status is "To Do" | 1. Task details are shown 2. Description is shown as "No Description Provided" in grey italic 3. Assignees is shown as "Unassigned" in grey italic 4. Status is "To Do" 5. BE returns 200 and task details
TC-PBI2-VIEW-TASK-DETAIL-3 | normal - non-English characters - taskStatus of "Doing" | TASK_BASE | 1. Open task details for task ดาต้าเบส 1.1 verify Title, Description and Assignees is non-English 1.2 verify Status is "Doing" | 1. Title, Details, and Assignees are shown in non-English characters correctly 2. Status is "Doing" 3. BE returns 200 and task details
TC-PBI2-VIEW-TASK-DETAIL-4 | normal - view different time zone - taskStatus of "Done" | TASK_BASE | 1. In task detail view for task _Infrastructure_ 2. change the browser's timezone to Australia/Sydney (+10:00) (see link on the right) 2.1 verify the time shown 2.2 verify Status is "Done" | 1. datetime is shown as 22/4/2024 19:15:00 (Australia/Sydney) and 22/4/2024 20:00:00 (Australia/Sydney) 2. Status is "Done" | https://www.browserstack.com/guide/change-time-zone-in-chrome-for-testing
TC-PBI2-VIEW-TASK-DETAIL-5 | failed - view task with invalid ID | TASK_BASE | 1. Open task view page at /task/100 | 1. FE shows User Appropriate message "The requested task does not exist" and when the message is closed redirects to the TaskList view (/task) 2. BE returns 404
TC-PBI3-ADD-TASK-BASIC-1 | normal - taskTitle is not entered - cancel the action |  | 1. Click "Add", FE shows a modal window to add a new task 2. Do not enter any field, verify that the task cannot be "Save". 3. Click "Cancel" | 1. FE shows a modal for adding new task 2. The "Save" button cannot be clicked. 3. When "Cancel" is clicked, returns to previous page. 4. FE does not send the request to BE
TC-PBI3-ADD-TASK-BASIC-2 | normal - optional fields - default status | TASK_BASE_ADD | 1. Click "Add", shows modal window 2. Add data TASK_BASE_ADD (5) 3. Click "Save" 4. Click on DevSecOps task title to view Details, verify task details | 1. FE does not send createdOn and updatedOn to BE 2. BE returns 200 and FE shows message "The task has been successfully added" 3. FE returns to Task Table view and shows DevSecOps task 4. Task Details show DevSecOps task, No Desciption Provided (in grey), Unassigned (in grey) and "No Status", current date and time for createdOn and updatedOn
TC-PBI3-ADD-TASK-BASIC-3 | normal - all fields - max size - To Do | TASK_BASE_ADD | 1. Click "Add", shows modal window 2. Add data TASK_BASE_ADD (6) 3. Click "Save" 4. Click on DevSecOps1… task title to view Details, verify task details | 1. FE shows message "The task has been successfully added" 2. FE returns to Task Table view and shows DevSecOps1... task 3. Task Details shows max character values for Title, Descriptin and Assignees, status is "To Do", and current date and time for createdOn and updatedOn
TC-PBI3-ADD-TASK-BASIC-4 | normal - trimmed - Done | TASK_BASE_ADD | 1. Click "Add", shows modal window 2. Add data TASK_BASE_ADD (7) 3. Click "Save" 4. Click on _Front End_ task title to view Details, verify task details | 1. FE shows message "The task has been successfully added" 2. FE returns to Task Table view and shows _FrontEnd_ task 3. Task Details shows title, description, and assignees have been trimmed. Status is "Done"
TC-PBI4-DELETE-TASK-1 | normal - cancel the action | TASK_BASE_ADD (con't from TC-PBI3) | 1. Click "Delete" for task DevSecOps 2. Click "Cancel" | 1. FE shows delete modal window for task DevSecOps with the message "Do you want to delete the task number 5 - DevSecOps?" 2. On "Cancel", FE does not send request to BE and returns to task table, task DevSecOps is still shown
TC-PBI4-DELETE-TASK-2 | normal - successful delete | TASK_BASE_ADD (cont) | 1. Click "Delete" for task DevSecOps1... 2. Click "Confirm" 3. Refresh the web page | 1. FE shows delete modal window for task DevSecOps1… with the message "Do you want to delete the task number 6 - DevSecOps1...?" 2. FE sends the request to BE. BE returns 200, FE shows message "The task has been deleted" 3. Closing message box returns to previous page. the Task Table view shows the task has been deleted 4. The deleted task is not shown after the refresh
TC-PBI4-DELETE-TASK-3 | failed - task(id) does not exist, e.g. has already been deleted by another user | TASK_BASE_ADD (cont) | 1. Open another tab/window, delete task '_Front End_'. 2. On your main tab, click 'Delete' task '_Front End_' and confirm deletion. | 1. On step 2, FE shows delete modal window with the message "Do you want to delete the task number 6 - _Front End_?" 2. After confirmation, FE shows message "The task does not exist", on close of message window, returns to previous page 3. BE returns 404
TC-PBI5-EDIT-TASK-BASIC-1 | normal - cancel the action | TASK_BASE_ADD (cont) | 1. Click "Edit" for task DevSecOps 2. Delete task title, verify that the changes cannot be saved 3. Click "Cancel" | 1. FE shows Edit task modal window prefilled with task details. All fields are editable except createdOn and updatedOn. 2. In step 1, the "Save" button is disable 3. When task title is deleted, changes cannot be saved 4. On "Cancel", FE does not send request to BE and return to previous page with DevSecOps task unchanged
TC-PBI5-EDIT-TASK-BASIC-2 | normal - all fields | TASK_BASE_ADD (cont) | 1. Click "Edit" for task DevSecOps 2. Change task title, description, and assignees to "DevSecOps2", and status to "Doing" 3. Click "Save" 4. Verify that task details have changed. | 1. FE shows Edit task modal window, all fields are editable except createdOn and updatedOn 2. FE shows "The task has been updated" 3. Task details show all fields as "DevSecOps2", status is "Doing", createdOn is unchanged, and updatedOn has been changed to the current time.
TC-PBI5-EDIT-TASK-BASIC-3 | normal - optional fields | TASK_BASE_ADD (cont) | 1. Click "Edit" for task DevSecOps2 2. Delete Description and Assignees fields, change status to "No Status" 3. Click "Save" 4. Verify that task details have changed. | 1. FE shows Edit task modal window, all fields are editable except createdOn and updatedOn 2. FE shows "The task has been updated" 3. Task Details show DevSecOps2 task title, No Desciption Provided (in grey), Unassigned (in grey) and "No Status", updatedOn has been changed to the current time
TC-PBI5-EDIT-TASK-BASIC-4 | failed - task(id) does not exist | TASK_BASE_ADD (cont) | 1. open task edit page for id(1000) | 1. FE shows message "The task does not exist", on close of message window, returns to previous page 2. BE returns 404
TC-PBI6-ADD-STATUS-1 | normal - add new status - cancel the operation | STATUS_BASE TASKS <empty table> | 0. prepare STATUS table with STATUS_BASE data, TASKS table is <empty>; open web browser Inspector tools 1. Click on "Manage Status" menu, FE shows 1) STATUS table 2. Click "Add", the FE shows 2) modal window to add new status 3. Enter "Test" for status name, FE 3) enables "Save" 4. Delete status name, FE 4) disable "Save" 5. Click "Cancel", Inspector shows 5) no request has been sent to BE 6. Click Refresh on browser window/tab to re-fetch data from BE and show 6) status table with no change | 1) FE shows status table with one status of "No Status" and Description "The default status"; shows options to Add, Edit, Delete 2) Add Status window provides options to Save and Cancel; the "Save" button is initially disabled 3) When statusName is entered, the "Save" button becomes enabled 4) When statusName is deleted, the "Save" button becomes disabled 5) on "Cancel", FE returns to previous window, view Inspector to show no request has been sent to BE 6) Before and after browser refresh, the Manage Status page shows the same table as in 1) above | STATUS table: No Status, To Do, Doing, Done
TC-PBI6-ADD-STATUS-2 | normal - add new status with no description | STATUS_BASE, STATUS_BASE_ADD, TASKS <empty table> | 1. From "Manage Status", FE shows 1) STATUS table 2. Click "Add" and enter SATUS_BASE_ADD (5) "Waiting" for status name, without entering a Description 3. Click "Save", Inspector shows 3) BE request/response messages 4. Click Refresh on browser window/tab to re-fetch data from BE and show 5) status table with "Waiting" status | 1) FE shows STATUS table with one status of No Status and its Description; has options to Add, Edit, Delete 2) "Save" button is enabled 3) on Save, Inspector shows request/response interactions with BE -request: statusName = "Waiting", Description = NULL -response: status code 201 and body 4) FE shows message "The status has been added" and return to previous page 5) Before and after browser refresh, the status table shows the Waiting status with no Description (show "No description is provided." in grey, italics) | STATUS table: No Status, To Do, Doing, Done add Waiting
TC-PBI6-ADD-STATUS-3 | normal - add new status with max field size | STATUS_BASE, STATUS_BASE_ADD, TASKS <empty table> | 1. From "Manage Status" page, click "Add" and enter test data details for STATUS_BASE_ADD (6) "Max..." for status name and status description; FE shows 1) with complete data 3. Click "Save", Inspector shows 2) BE request/response messages 4. Click Refresh on browser window/tab to re-fetch data from BE and show 4) updated status table | 1) on Add Status page, FE shows statusName and statusDescripton fields with complete test data. 2) on Save, Inspector shows request/response interactions with BE -request: statusName = "Max...", statusDescription = "Max..." -response: status code 201 and body 3) FE shows "The status has been added" and return to previous page 4) Before and after browser refresh, the status table shows the Max... status has been added with Max... Description | STATUS table: No Status, To Do, Doing, Done, Waiting add Max…
TC-PBI6-ADD-STATUS-4 | normal - all fields with leading and trailling whitespace | STATUS_BASE, STATUS_BASE_ADD, TASKS <empty table> | 1. From "Manage Status" page, click "Add" and enter test data details for STATUS_BASE_ADD (7) " _trim_ " for status name and status description; FE shows 1) with complete data 3. Click "Save", Inspector shows 2) BE request/response messages 4. Click Refresh on browser window/tab to re-fetch data from BE and show 4) updated status table | 1) on Add Status page, FE shows statusName and statusDescripton fields with trimmed test data. 2) on Save, Inspector shows request/response interactions with BE -request: statusName = "_trim_", statusDescription = "_trim_" -response: status code 201 and body 3) FE shows "The status has been added" and return to previous page 4) Before and after browser refresh, the status table shows the _trim_ status has been added with _trim_ Description
TC-PBI6-ADD-STATUS-5 | normal - add 3 tasks with No Status and To Do status | STATUS_BASE_ADD TASKS_BASE | 1. On TaskView page, click "Add", shows modal window 2. Add data task TaskTitle... with status "No Status" from TASK_BASE (1), click "Save"; FE shows 1) 3. On TaskView page, click "Add", shows modal window 4. Add data task Repository (TASK_BASE (2)) and ดาต้าเบส (TASK_BASE (3)) , choose status "Waiting" for both tasks; click "Save"; 5. Click Refresh on browser window/tab to re-fetch data from BE and show 5) updated TaskView page | 1) on Add Task window, the task TaskTitle… is shown with default status of No Status 2) on Save, return to TaskView page 2.1) Inspector shows request/reponse -request: body with TaskTitle... data with "No Status" status (statusId=1) -response: status code 201, response body 3) on Add Task window, the task <Repository ¦ ดาต้าเบส> is shown and can choose "Waiting" for status 3.1) Inspector shows request/response -request: body with <Reposity¦ดาต้าเบส> task data with "Waiting" status (statusId=5) -response: status code 201, response body 4) on Save, return to TaskView page 5) Task table is shown with the three added tasks with statuses No Status and Waiting | STATUS table: No Status, To Do, Doing, Done, Waiting, Max, _Trim_ TASKS table: Add TaskTile…, No Status Repository, Waiting ดาต้าเบส, Waiting
TC-PBI7-EDIT-STATUS-1 | normal - cannot edit No Status - enable Save on edit - cancel edit | STATUS_BASE and STATUS_BASE_ADD (cont. from TC-PBI6) | 1. From "Manage Status" page, click "Edit" for No Status status, FE shows 1) message 2. click "Edit" for To Do status, FE shows 2) StatusEdit modal window 3. change status name to "Not To Do", FE shows 3) enable Save button 4. Click "Cancel", FE shows 3) Status Table with no change, Inspector shows that no request has been submited | 1) On Edit of No Status, FE does not allow edit of 'No Status' status, either by disabling edit button or showing a message "This status is the default status and cannot be modified" and returns to previous window 2) on Edit of To Do status, FE shows EditStatus modal window with statusName and statusDescription being editable; has options to "Save" (initially disabled) and "Cancel" 3) Save becomes enabled after statusName has been edited 4) on Cancel, FE returns to previous page with 7 statuses without changing To Do status name, Inspector shows that no request has been sent to BE | STATUS table: No Status, To Do, Doing, Done, Waiting, Max TASKS table: TaskTile…, No Status Repository, Waiting ดาต้าเบส, Waiting
TC-PBI7-EDIT-STATUS-2 | normal - edit statusName and statusDescription - Name and Description with leading and trailing whitespaces | STATUS_BASE and STATUS_BASE_ADD (cont) | 1. From "Manage Status" page, click "Edit" for Waiting status, FE shows 1) StatusEdit modal window 2. change status name to: " _Dropped_ ", and description to: " _Tasks are no longer needed_ " 3. Click "Save", Inspector shows 2) request/response with BE 4. Click Refresh on browser window/tab to re-fetch data from BE and show 3) updated Status Table 5. Open TaskView page, FE shows 4) updated Task Table | 1) on Edit, FE shows StatusEdit window with all fields editable 2) on Save, FE sends request to BE, - request: statusName = "_Dropped_", Description = "_Tasks are no longer needed_" - response: status code 200; body FE shows message "The status has been edited" 3) FE shows updated Status Table with _Dropped_ status 4) FE shows Task Table with 3 tasks: TaskTitle… with No Status status; Repository and ดาต้าเบส with _Dropped_ status | STATUS table: No Status, To Do, Doing, Done, Waiting, Max, _Trim_ Edit: Waiting >> _Dropped_ TASKS table: TaskTile…, No Status Repository, Waiting >> _Dropped_ ดาต้าเบส, Waiting >> _Dropped_
TC-PBI7-EDIT-STATUS-3 | normal - edit statusDescription only | STATUS_BASE and STATUS_BASE_ADD (cont) | 1. From "Manage Status" page, click "Edit" for Max... status, FE shows 1) StatusEdit modal window 2. Delete status description; FE shows 2) edited values 3. Click "Save", Inspector shows 3) request/response with BE 4. Click Refresh on browser window/tab to re-fetch data from BE and show 4) updated Status Table | 1) on Edit, FE shows StatusEdit window with all fields editable 2) statusName is unchanged, statusDescription is <not specified - NULL> 3) on Save, FE sends request to BE - request: statusName = "Max..."; statusDescription = NULL - response: status code 200; body 4) FE shows updated Status Table with Max... status with no Description (show "No description is provided." in grey, italics) | STATUS table: No Status, To Do, Doing, Done, _Dropped_, Max, _Trim_ Edit: Max >> Max : Null TASKS table: TaskTile…, No Status Repository, Dropped ดาต้าเบส, Dropped
TC-PBI7-EDIT-STATUS-4 | failed - status(id) does not exist | none | 1. Open status edit page for status(id=1000) 2. (If cannot test on FE) BE: setup API request (Swagger or Postman) to BE endpoint for edit status with "TestStatus" for statusName and non-existing statusID "status(id)=1000" 2. Send request, Swagger/Postman shows 2) BE response message | 1. FE shows message "An error has occurred, the status does not exist.", on close of message window, returns to previous page. BE returns 404 2) BE response message - status code: 404 and appropriate message "The requested status does not exist"
TC-PBI8-DELETE-STATUS-1 | normal - cannot delete No Status - cancel delete status | STATUS_BASE_ADD TASKS_BASE (cont. from TC-PBI7) | 1. Open Manage Status page, FE shows 1) 2. Click "Delete" the No Status status, FE shows 2) 3. Click "Delete" the "Max" status, FE shows 3) confirmation modal window with message 4. Click "Cancel", FE returns to 4) previous page | 1) Manage Status page shows statuses as on the right >> 2) FE does not allow delete of 'No Status' status, either by disabling edit button or showing a message "This status is the default status and cannot be modified" and returns to previous window 2) on Delete of Max... status, FE shows modal window "Do you want to delete Max... status?" with options to "Confirm" and "Cancel"; 3) on Cancel, FE returns to the Manage Status page, Inspector shows that no request was made to BE | STATUS table: No Status, To Do, Doing, Done, _Dropped_, Max, _Trim_ TASKS table: TaskTile…, No Status Repository, _Dropped_ ดาต้าเบส, _Dropped_
TC-PBI8-DELETE-STATUS-2 | normal - delete status with no task | STATUS_BASE_ADD TASKS_BASE (cont. from TC-PBI7) | 1. on Manage Status page, click "Delete" the Max status, FE shows 1) confirmation modal window with message 2. click "Confirm Deletion", FE shows 3) message, Inspector shows request/response 3. refresh the Manage Status page, FE shows 4) | 1) on Delete of Max... status, FE shows modal window "Do you want to delete Max... status?" with options to "Confirm" and "Cancel"; 2) on "Confirm", FE sends request to BE, Inspector shows request/response - response: status code 200; body 3) FE shows message "The status has been deleted" 4) ManageStatus page shows statuses of No Status, To Do, Doing, Done, _Dropped_, _Trim_ | STATUS table: No Status, To Do, Doing, Done, _Dropped_, Max, _Trim_ Delete: Max TASKS table: TaskTile…, No Status Repository, _Dropped_ ดาต้าเบส, _Dropped_
TC-PBI8-DELETE-STATUS-3 | normal - delete status with task(s) - transfer task(s) to another status | STATUS_BASE_ADD TASKS_BASE | 1. From Manage Status page, click "Delete" the _Dropped_ status, FE shows 1) delete confirmation modal window with message 2. Choose Doing as the status to transfer to 3. Click "Transfer and Delete", FE shows 3) message 4. Open TaskView page, FE shows 4) task with new status | 1) on Delete of _Dropped_ status, FE shows modal window "There are 2 tasks in _Dropped_ status. In order to delete this status, the system must transfer tasks in this status to existing status. Transfer tasks to [drop-down of No Status, To Do, Doing, Done, _Trim_] " with options to "Transfer and Delete" and "Cancel"; 1.1) _Dropped_ is not listed in the drop-down 1.2) Doing is shown as the status to transfer to 2) on Confirm Delete, FE sends request to BE, Inspector shows request/response with BE - request: to-delete status: _Dropped_ ; destination status: Doing - response: status code 200; body 3) FE shows message "2 task(s) have been transferred and the status has been deleted" and return to previous page 4) the Task Table shows 2 tasks: TaskTitle..., No Status and Repository, Doing; ดาต้าเบส, Doing | STATUS table: No Status, To Do, Doing, Done, _Dropped_, _Trim_ Delete: _Dropped_ >> Change to: Doing TASKS table: TaskTile…, No Status Repository, _Dropped_ >> Doing ดาต้าเบส, _Dropped_ >> Doing
TC-PBI8-DELETE-STATUS-4 | failed - try to delete the same status twice | STATUS_BASE_ADD TASKS_BASE | 0. Open two tabs to the Manage Status page 1. Click "Delete" the Doing status on both tabs, FE shows 1) delete confirmation modal window with message 2. Choose No Status as the status to change to on both tabs 3. On the first tab, Click "Transfer and Delete", FE shows 3) message 4. On the second tab, click "Transfer and Delete", FE shows 4) error message | 1) on Delete of Doing status, FE shows modal window "There are 2 tasks in Doing status. In order to delete this status, the system must transfer tasks in this status to existing status. Transfer tasks to [drop-down of No Status, To Do, Done, _Trim_] " with options to "Transfer and Delete" and "Cancel"; 1.1) Doing is not listed in the drop-down 1.2) No Status is shown as the status to transfer to 2) on Confirm Delete, FE sends request to BE, Inspector shows request/response with BE - request: to-delete status: Doing; destination status: No Status - response: status code 200; body 3) FE shows message "2 task(s) have been transferred and the status has been deleted" and return to previous page. The Manage Status page shows 4 statuses: No Status, To Do, Done, _Trim_ 4) BE responds with status code 404, body; FE shows error message "An error has occurred, the status does not exist." and return to previous page | STATUS table: No Status, To Do, Doing, Done, _Trim_ Delete: Doing >> No Status Delete: Doing >> ERROR TASKS table: TaskTile…, No Status Repository, Doing >> No Status ดาต้าเบส, Doing >> No Status
TC-PBI9-NESTED-PUBLIC-PATH-1 | normal - access FE, BE on public url |  | 1. FE URL: http://intproj23.sit.kmutt.ac.th/<TEAMCODE>/task 1.1 Open Inspector 1.2 View task details, and add/edit/delete task to verify all functions 2. BE URL: http://intproj23.sit.kmutt.ac.th:8080/<TEAMCODE>/v2/tasks or http://intproj23.sit.kmutt.ac.th/<TEAMCODE>/api/v2/tasks | 1) FE shows task table, listing all tasks 1.1) can view/add/edit/delete tasks correctly 1.2) FE must fetch own API on intproj23 only 2) BE sends response to /tasks
TC-PBI10-SORT-TASK-BY-STATUS-TABLE-VIEW | normal - sort alphabetical, reverse - return to default | STATUS_SORT_FILTER TASK_SORT_FILTER | 0. from empty DB, add tasks from TASK_SORT_FILTER, and add statuses from STAUS_SORT_FILTER 1. On Task Table View page, click on "Sort" to sort by status name 2. Click on "Sort" again to reverse sort order 3. Click on "Reset" to return to default sorting order | 1) The task table is sorted in status-alphabetical order by status >> see expected output 2) The task table is sorted in reverse alphabetical order 3) The task table returns to default sort order (by createDate) | After Step 1) DO01 Done IP01 In Progress IP02 In Progress NS01 No Status TD01 To Do TD02 To Do
TC-PBI11-FILTER-TASK-BY-STATUS-1 | normal - filter by one status - filter by multiple statues - filter and sort | cont. from PBI10 | 1. click on "Sort" to sort status by alphabetical order 2. click "Filter" and choose "To Do" 3. click "Filter and choose "In Progress" 4. click "Filter", choose all statuses | 1) The task table sorts by status-alphabetical order 2) The task table shows only tasks in the "To Do" status 3) The task table shows tasks in "In Progress" and "To Do" in status-alphabetical order 4) The task table shows tasks in all statuses | After Step 3) IP01 In Progress IP02 In Progress TD01 To Do TD02 To Do
TC-PBI11-FILTER-TASK-BY-STATUS-2 | normal (BE) - filter by invalid status | cont. from PBI10 | 1. postman sends request to filter with invalid statusID {1000} 2. postman sends request to filter with statusID {1000} and To Do{2} | 1) response code 200, and empty array 2) response code 200, and array of TD01 and TD02 tasks in To Do status
TC-PBI11-FILTER-TASK-BY-STATUS-3 | failed (BE) - filter by other field | cont. from PBI10 | 1. postman sends request to filter task by taskAssignees | 2) BE does not filter, returns 400 and message "invalid filter parameter"
TC-PBI12-LIMIT-TASKS-IN-STATUS-1 | normal - limit disabled - enable limit, then cancel - enable then disable limit - add/edit task <= limit - add/edit task > limit - delete status and transfer > limit | cont. from PBI11 TASK_LIMIT_BASE TASK_LIMIT_ADD | 0. add tasks from TASK_LIMIT_BASE 1. On Status Management page, click "Enable" limit, and "Cancel" 2. click "Enable" limit, confirm enable; then click "Disable" limit, confirm disable 3. Add In limit: Add task TD10 from TASK_LIMIT_ADD 4. Add over limit: Add task IP11 from TASK_LIMIT_ADD 5. Edit over limit: Edit task TD10, change status to "In Progress" 6. Edit in limit: Edit task IP11, change status to "To Do" 7. Delete status "Waiting" and transfer tasks to status "To Do" | 1) On click Enable, FE shows Limit Enable modal/page, with options to "Confirm" and "Cancel", and show message "The Kanban board will limit the number of tasks in each status to 10." On "Cancel" task limit in status remains Disable, no request is sent to BE. FE returns to previous page. 2.1) On confirm Enable, show message "The kanban board now limits 10 tasks in each status". FE sends request to BE with response status 200. FE shows limit status as "Enable" on status management page. 2.2) on limit "Disable" , show message "The kanban board has disabled the task limit in each status". FE sends request to BE with response status 200. FE shows limit status as "Disable" 3) "To Do" status has 10 tasks 4) "In Progress" status has 11 tasks 5) Task TD10 is moved to "In Progress" with 12 tasks 6) Task IP11 is moved to "To Do" with 10 tasks, "In Progress" has 11 tasks 7) Task WA01 is transfered to "To Do" with 11 tasks, "Waiting" status is deleted
TC-PBI12-LIMIT-TASKS-IN-STATUS-2 | normal - limit enabled - add/edit task in No Status and Done > limit - add/edit task in other statuses >= limit - delete status and transfer to < limit status - delete status and transfer to >= limit status | cont. | 1. Enable limit, confirm 2. Add over limit No Status and Done: on Task View page, Add task NS11 and DO11 from TASK_LIMIT_ADD 3. Edit over limit Done: Edit task IP01 and IP02, change status to "Done" 4. Edit over limit No Status: Edit task TD09, change status to "No Status" 5. Edit in limit: edit TD01, change status to "In Progress" 6. Edit over limit: edit TD02, change status to "In Progress" 7. Add In limit: Add task TD11 from TASK_LIMIT_ADD 8. Add over limit: Add task TD12 from TASK_LIMIT_ADD 9. Edit IP03, change status to "Done" 10. Delete status "Testing" and transfer tasks to status "In Progress" 11. Delete status "Reviewing" and transfer tasks to status "In Progress". Choose "Cancel" | 1) limit is Enabled: show message limit has been enabled, show status enable. 2) No Status and Done tasks each have 11 tasks 3) IP01 and IP02 are moved to "Done" status with 13 tasks; "In Progress" now has 9 tasks 4) TD09 is moved to "No Status" status with 12 tasks; "To Do" now has 10 tasks 5) TD01 is moved to "In Progress" status with 10 tasks; "To Do" now has 9 tasks 6) cannot edit TD02, FE shows "The status In Progress will have too many tasks. Please make progress and update status of existing tasks first.". TD02 is still in "To Do" status. 7) TD11 is added and "To Do" now has 10 tasks 8) cannot add TD12, FE shows "The status To Do will have too many tasks. Please make progress and update status of existing tasks first.". TD12 is not in the task table. 9) IP03 is moved to "Done" status with 13 tasks; "In Progress" now has 9 tasks 10) Task WA01 is transfered to "In Progress" with 10 tasks, "Testing" status is deleted 11) cannot delete "Reviewing", show message "Cannot transfer to In Progress status since it will exceed the limit. Please choose another status to transfer to." FE returns/stays on "transfer and delete" modal. On "Cancel" return to previous page (Status Management) |  | TD02 | To Do
TC-PBI12-LIMIT-TASKS-IN-STATUS-3 | normal - disable limit - delete status and transfer to > limit status | cont. | 1. Disable Limit 2. Delete status "Reviewing" and tranfer tasks to "In Progress" | 1) on Disable, show message, show limit status as Disable 2) status "Reviewing" is deleted, 1 task is transferred to "In Progress" which now has 11 tasks
TC-PBI13-VALIDATE-INPUT-FE-BASIC-1 | normal - tasks - add/edit exceed max field size | TASK_ADD_>MAX | 1. Add taskID{46} TaskTitle…, from TASK_ADD_>MAX copy and paste TaskTitle and taskDescription fields 1.1 Edit data to maxSize and save 2. Edit task TaskTitle…, copy and paste TaskTitle and taskDescription fields 2.1 Edit data to maxSize and save | 1) FE pastes all input, but does not allow save until data has been edited to be within max size for both fields. (NOTE: if you handle this differently, discuss with advisor). 1.1) task is added to "No Status" 2) on paste, cannot Save; 2.1) after edit data, task can be Save and data updated
TC-PBI13-VALIDATE-INPUT-FE-BASIC-2 | normal - statuses - cannot add/edit non-unique statusName - cannot edit/delete "Done" - add/edit exceed max field size | STATUS_ADD_>MAX | 1. add status "In Progress", and Save. cancel add status 2. edit status "To Do", change to "No Status". cancel edit status 3. FE does not have button to Edit/Delete status "Done" 4. Add statusID{8} Max… from STATUS_ADD_>MAX, copy and paste statusName and statusDescription fields 4.1 Edit data to maxSize and save 5. Edit status Max…, copy and paste statusName and statusDescription fields from STATUS_ADD_>MAX 5.1 Edit data to maxSize and save | 1) on Save, FE shows message "Status name must be uniques, please choose another name.", stay on add modal. On cancel, FE returns to previous page 2. on Save, FE shows message "Status name must be uniques, please choose another name.", stay on edit modal. On cancel, FE returns to previous page 3) cannot choose to Edit / Delete status "Done" 4) FE pastes all input, but does not allow save until data has been edited to be within max size for both fields. (NOTE: if you handle this differently, discuss with advisor). 4.1) status Max... is added 5) on paste, cannot Save; 5.1) after edit data, status can be Save and data updated
TC-PBI13-VALIDATE-INPUT-BE-BASIC-1 | failed - task - add/edit no taskTitle - add/edit exceed max field size - add/edit task to invalid status | TASK_ADD_>MAX | 1. PostMan: send Add task request with no taskTitle provided, use description "No task title" 2. PostMan: send Edit task request for taskID{1} with empty taskTitle, change description to "No task title" 3. PostMan: send Add task request: use data from TASK_ADD_>MAX taskID{46} 4. PostMan: send Edit task request for taskID{1}, use data from TASK_ADD_>MAX 5. PostMan: send Add task request with taskTItle "Invalid Status", no description and statusID{1000} 6. PostMan: send Edit task request for task NS01{1} with taskTitle "Invalid Status", statusID{1000} | 1) BE does not add task, return 400 and message {"field": "title", "must not be null"} 2) BE does not edit task, return 400 and message {"field": "title", "must not be null"} 3) BE does not add task, return 400 and message "<fieldName> size must be between ..." 4) BE does not edit task, return 400 and message "<fieldName> size must be between ..." 5) BE does not add task, return 400 and message {"field": "status", "message": "does not exist"} 6) BE does not edit task, return 400 and message {"field": "status", "message": "does not exist"}
TC-PBI13-VALIDATE-INPUT-BE-BASIC-2 | failed - status - edit/delete "No Status" and "Done" - add/edit with no statusName - add/edit exceed max field size | STATUS_SORT_FILTER (cont.) STATUS_ADD_>MAX | 1. PostMan: send Edit request for "No Status" {1} and then send Edit request for "Done" {6}, change statusName to "new name" 2. PostMan: send Delete request for status "No Status" {1} and "Done" {6} 3. PostMan: send Add status request with no statusName provided, use "No status name" as description 4. PostMan: send Edit status request for status "In Progress" {3} with empty statusName and change description to "No status name" 5. PostMan: send Add status request: use data from STATUS_ADD_>MAX status Max... {7} 6. PostMan: send Edit status request for "In Progress" {3}, use data Max... {7} | 1) BE does not edit "No Status" and "Done", return 400 and message "No Status cannot be modified." and "Done cannot be modified." respectively. 2) BE does not delete "No Status" and "Done", return 400 and message "No Status cannot be deleted." and "Done cannot be deleted." respectively. 3) BE does not add new status, return 400 and message {"field": "name", "message": "must not be null"} 4) BE does not edit status, return 400 and message {"field": "name", "message": "must not be null"} 5) BE does not add status, return 400 and message {"field": "<field name>", "message": "must be between ..."} for each field. 6) BE does not edit status, return 400 and message {"field": "<field name>", "message": "must be between ..."} for each field.
TC-PBI13-VALIDATE-INPUT-BE-BASIC-3 | failed - status - add/edit status with non-unique name | cont. | 1. PostMan: send Add status request with statusName "In Progress" 2. PostMan: send Edit status request "In Progress" {3} change statusName to "No Status" | 1) BE does not add status, return 400 and message {"field": "name", "message": "must be unique"} 2) BE does not edit status, return 400 and message {"field": "name", "message": "must be unique"}
TC-PBI13-VALIDATE-INPUT-BE-BASIC-4 | failed - status -delete status with tasks (not transferred) -transfer task to invalid status -transfer task to same status | cont. | 1. PostMan: send Delete status request for "In progress" {3} without specifying destination status for transferring tasks 2. PostMan: send Delete status and Transfer request for "In Progress" {3} transfer tasks to statusID{1000} 3. PostMan: send Delete status and Transfer request for "In Progress" {3} and transfer to "In Progress" {3} | 1) BE does not delete status, return 400 and message "destination status for task transfer not specified." 2) BE does not delete status, return 400 and message "the specified status for task transfer does not exist." 3) BE does not delete status, return 400 and message "destination status for task transfer must be different from current status"

## TEST-Partitioning
PBI12-LIMIT-TASKS-IN-STATUS
Limit |  | Add Task Status |  | Edit Task Status |  | Delete Task | Delete Status and Transfer |  |  | Result
Off | On | > Limit | <= Limit | > Limit | <= Limit | numTask-1 | No | <= Limit | > Limit
| x | x |  | x |  | x |  |  |  | cannot add/edit, stay on modal, user "Cancel"
| x |  | x |  | x |  |  |  |  | success
| x | [5 empty] | x |  |  | success
| x | [6 empty] | x |  | success
| x | [7 empty] | x | cannot Delete, stay on Delete/Transfer Page, user "Cancel"
x | [6 empty] | x |  |  | success
x | [7 empty] | x |  | success
x | [8 empty] | x | success
x |  | x |  | x |  | x |  |  | x | success
x |  |  | x |  | x |  |  |  |  | success
PBI11-FILTER-TASKS-BY-STATUS
Filter |  | No. of Status |  | StatusValid? (BE)
off | on | Single | Multiple | Yes | No
| x | x |  | x
| x | x |  |  | x
| x |  | x | x
| x |  | x |  | x
| x |  | x | x | x
x

## API Spec
Swagger UI (kmutt.ac.th)
API Specifications for sprint-1 (update-1)
http://ip23<TEAM-CODE>.sit.kmutt.ac.th
Server:
URI:
API Specifications for sprint-2
API Specifications for sprint-3
API Specifications for sprint-4
http://intproj23.sit.kmutt.ac.th/<TEAMCODE>/api
Server: